## Sprint1
Week #1 (7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-08 | 2021-10-09 | 2021-10-10 | 2021-10-11 | 2021-10-12 | 2021-10-13 | 2021-10-14
28
Learning technologies, ER diagram, Architecture | Requirement Analysis | All | 6 | 4 | 4 | 2 | 0 | 0 | 0 | 0
| Research on tech stack | All | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| Tech stack finalzation | All | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| ER- diagram | All | 5 | 5 | 5 | 5 | 2 | 2 | 1 | 0
| Architecture | All | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 0
| Environment setup | All | 5 | 5 | 5 | 4 | 2 | 0 | 0 | 0
|  | Total | 28 | 24 | 23 | 19 | 8 | 5 | 3 | 0
Team
| Aniruddha Narkhede | 7 hours/week
| Sakshi Kasat | 7 hours/week
| Siddh Patel | 7 hours/week
| Sudheendra Katekar | 7 hours/week
| Total | 28

## Sprint2
Week #2 ( 7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-15 | 2021-10-16 | 2021-10-17 | 2021-10-18 | 2021-10-19 | 2021-10-20 | 2021-10-21
28
Database creation for flight and users, CRUD APIs for flight, CRUD APIs for Users, Front end mock ups | Learning Node JS | Sudheendra | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0
| Learn mongoose | Sudheendra | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| Learning Node JS | Sakshi | 7 | 7 | 6 | 3 | 3 | 1 | 0 | 0
| Learning ReactJS and MUI | Siddh | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| Frontend for flight detail page | Siddh | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0
| Techstack revamp | All | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| ER- diagram | Aniruddha | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Mongo KT | Aniruddha | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 0
|  | Total | 28 | 27 | 22 | 14 | 10 | 4 | 2 | 0
Team
| Aniruddha Narkhede | 7 hours/week
| Sakshi Kasat | 7 hours/week
| Siddh Patel | 7 hours/week
| Sudheendra Katekar | 7 hours/week
| Total | 28

## Sprint3
Week # 3( 7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 5 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-22 | 2021-10-23 | 2021-10-24 | 2021-10-25 | 2021-10-26 | 2021-10-27 | 2021-10-28
20
User Login back end,User Sign up back end, Login screen, Sign up screen, Authorization, API for flight search, Flight seach UI | APIs for user login, signup | Sudheendra | 5 | 5 | 5 | 4 | 3 | 1 | 0 | 0
| CRUD APIs for dummy flight | Sakshi | 5 | 5 | 4 | 3 | 3 | 3 | 2 | 0
| Front end for SIgnIn/SignUp | Siddh | 5 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| Database population | Aniruddha | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0
| Angular KT | Aniruddha | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 20 | 17 | 14 | 11 | 7 | 4 | 2 | 0
Team
| Aniruddha Narkhede | 7 hours/week
| Sakshi Kasat | 7 hours/week
| Siddh Patel | 7 hours/week
| Sudheendra Katekar | 7 hours/week
| Total | 28

## Sprint4
Week #4 ( 7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-10-29 | 2021-10-30 | 2021-10-31 | 2021-11-01 | 2021-11-02 | 2021-11-03 | 2021-11-04
28
| Login api to return user token | Sudheendra | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0
User miles, Flight search issue, API development for booking, seat map front end, seat map back end | Auth token integration | Sudheendra | 3 | 3 | 3 | 3 | 2 | 1 | 0 | 0
| Flight search by source and dest | Sakshi | 5 | 5 | 5 | 5 | 5 | 4 | 3 | 3
| Modify flight search query | Sakshi | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Frontend for Flight list | Siddh | 5 | 5 | 3 | 1 | 0 | 0 | 0 | 0
| Modified SignIn/SignUp page | Siddh | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Signup api | Aniruddha | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Miles rewards logic | Aniruddha | 5 | 5 | 5 | 5 | 4 | 3 | 2 | 0
|  | Total | 28 | 28 | 25 | 21 | 14 | 8 | 5 | 3
Team
| Aniruddha Narkhede | 7 hours/week
| Sakshi Kasat | 7 hours/week
| Siddh Patel | 7 hours/week
| Sudheendra Katekar | 7 hours/week
| Total | 28

## Sprint5
Week #5 ( 7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-11-05 | 2021-11-06 | 2021-11-07 | 2021-11-08 | 2021-11-09 | 2021-11-10 | 2021-11-11
28
User info display, Seat map api and UI integration, Fix defects, Testing the flight search, test the date defects, Deployment to AWS | Cancel booking route | Sudheendra | 3 | 3 | 3 | 2 | 1 | 0 | 0 | 0
| Update booking api | Sudheendra | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0
| Refactored user info route | Sudheendra | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| Fix issue for flight search in front end | Sakshi | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0
| API modification for flight search | Sakshi | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0
| Research regarding how to make flight seat selection | Siddh | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| Flight seat selection page | Siddh | 3 | 3 | 3 | 3 | 2 | 2 | 0 | 0
| Testing | Siddh | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Fetch user miles | Aniruddha | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Adding user profile dashboard | Aniruddha | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| Sanity and regression testing | Aniruddha | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
| Fixed query syntax | Aniruddha | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0
|  | Total | 28 | 28 | 21 | 15 | 6 | 4 | 1 | 0
Team
| Aniruddha Narkhede | 7 hours/week
| Sakshi Kasat | 7 hours/week
| Siddh Patel | 7 hours/week
| Sudheendra Katekar | 7 hours/week
| Total | 28

## Sprint6
Week #6 ( 7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-11-12 | 2021-11-13 | 2021-11-14 | 2021-11-15 | 2021-11-16 | 2021-11-17 | 2021-11-18
28
Seat reservation, UI beautification, Status, check-in components in UI, Payment functionality, End to end testing, deplyment to AWS | Book rocket functions | Sudheendra | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| User profile dashboard | Sudheendra | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0
| Seat map api | Sudheendra | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Testing | Sudheendra | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0
| Fix the Date issue in backend | Sakshi | 5 | 5 | 4 | 0 | 0 | 0 | 0 | 0
| Frontend for Seat selection | Siddh | 4 | 4 | 2 | 1 | 0 | 0 | 0 | 0
| Drawer to check user trips and information | Siddh | 3 | 3 | 3 | 3 | 1 | 0 | 0 | 0
| Integrate the date logic to front end | Sakshi | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0
| Updated seat class | Aniruddha | 3 | 3 | 2 | 1 | 0 | 0 | 0 | 0
| User account dashboard | Aniruddha | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0
| Testing | Aniruddha | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0
| Production build | Aniruddha | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
|  | Total | 28 | 28 | 20 | 12 | 5 | 2 | 2 | 0
Team
| Aniruddha Narkhede | 7 hours/week
| Sakshi Kasat | 7 hours/week
| Siddh Patel | 7 hours/week
| Sudheendra Katekar | 7 hours/week
| Total | 28

## Sprint7
Week #7 ( 7 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 7 x 4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2021-11-19 | 2021-11-20 | 2021-11-21 | 2021-11-22 | 2021-11-23 | 2021-11-24 | 2021-11-25
28
| Reserve seat after booking | Sudheendra | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
| Rocket status, checkin components | Sudheendra | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0
| Toggling flight seats on reserve/cancel | Sudheendra | 3 | 2 | 2 | 2 | 2 | 2 | 1 | 1
| API: Get user info by ID | Sakshi | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0
| UI Modification with Icon | Sakshi | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| Testing map selection functionality | Sakshi | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0
| Merged API to find flights | Siddh | 3 | 3 | 1 | 0 | 0 | 0 | 0 | 0
| Merged SignIn/SignUp API with frontend | Siddh | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0
| Frontend for Payment | Siddh | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
| Updated toggle seat function | Aniruddha | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 0
| Adding payment method | Aniruddha | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0
| Fixed signup message alert | Aniruddha | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
| End to end product testing | Aniruddha | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1
|  | Total | 28 | 27 | 21 | 15 | 12 | 5 | 4 | 2
Team
| Aniruddha Narkhede | 7 hours/week
| Sakshi Kasat | 7 hours/week
| Siddh Patel | 7 hours/week
| Sudheendra Katekar | 7 hours/week
| Total | 28